# LAMP ASSESSMENT PRACTICES SUB-COMMITTEE

# Action Plan

# December 9, 2008 (DRAFT)

## Purpose

The Assessment Practices Sub-committee’s (APS) primary responsibility is to:

- Gather information related to assessment practices at Missouri institutions

- Interpret this data and create a relevant report to inform policy decisions related to a statewide assessment policy

## Action Plan

The depth and breadth of assessment practices across the state cannot be underestimated.  In order to understand the complexities of these issues the APS intends the following:

- Survey perceptions of assessment culture on Missouri campuses and current attitudes regarding statewide collaboration and key policy issues

- Interview institutional representatives in charge of assessment policy and practice about the details of assessment processes and instruments at their campus.  These interviews are designed not only to provide a catalog of assessment instruments but provide extensive information related to:

  - Methodology

  - How information is used

  - Perceived effectiveness, and

  - Policy implications

The interviews will focus upon the key academic transition points identified in LAMP’s Policy Guidance.

The implementation strategy for fielding the survey and interviews is yet to be decided.

- The sub-committee will create a report detailing key findings related assessment practice across the state, as well as, recommendations of the significance of the findings for specific policy issues.  A draft of this report will be completed prior to the March 2009 deadline for discussion of policy recommendations.

## Timeline

(dates tentative!)  When need to meet?

November

12	APS Organizational Meeting

December

10	APS Meeting to review action plan and proposed strategy for survey and interview of assessment culture and practice

15	Field survey of assessment culture

January

19	Begin assessment practices interviews

23	Deadline for returning survey of assessment culture

February

13	Complete Interview Phase

16-27	Analysis of Data and Draft Report